## Sprints
Document version
No | Updates | Name | Date | Version
1 | Start of Sprint 1 | Then Kah Nyee | 2023-07-03 | version0.1
2 | Updates on Sprint_Planning with product backlog ID-1 to ID-4 done | Then Kah Nyee , Ong Shern Wen Benjamin, Tan Xing Yu Jayden, Chen Jian Cong, Wong Zi Yang | 2023-07-10 | version0.2
3 | Updates on Sprint_Planning with product backlog ID-1 to ID-6 done | Then Kah Nyee , Ong Shern Wen Benjamin, Tan Xing Yu Jayden, Chen Jian Cong, Wong Zi Yang | 2023-07-10 | version0.3
4 | Updates on Sprint_Planning with product backlog ID-1 to ID-10 done | Then Kah Nyee , Ong Shern Wen Benjamin, Tan Xing Yu Jayden, Chen Jian Cong, Wong Zi Yang | 2023-07-15 | version0.4
5 | End of Sprint 1 and Updates on Sprint_Planning for Sprint 2 | Then Kah Nyee , Ong Shern Wen Benjamin, Tan Xing Yu Jayden, Chen Jian Cong, Wong Zi Yang | 2023-07-16 | version0.5
6 | Start of Sprint 2 | Tan Xing Yu Jayden | 2023-07-17 | version1.0
7 | Updates on Sprint_Planning with product backlog ID-1 to ID-13 done and Updates on Sprint_Planning for Sprint 3 | Then Kah Nyee , Ong Shern Wen Benjamin, Tan Xing Yu Jayden, Chen Jian Cong, Wong Zi Yang | 2023-07-29 | version1.1
8 | Updates on Sprint_Planning with product backlog ID-1 to ID-18 done | Then Kah Nyee , Ong Shern Wen Benjamin, Tan Xing Yu Jayden, Chen Jian Cong, Wong Zi Yang | 2023-07-29 | version1.2
9 | End of Sprint 2 | Then Kah Nyee , Ong Shern Wen Benjamin, Tan Xing Yu Jayden, Chen Jian Cong, Wong Zi Yang | 2023-07-30 | version1.3
10 | Start of Sprint 3 | Chen Jian Cong | 2023-07-31 | version2.0
11 | Updates on Sprint_Planning with product backlog ID-1 to ID-27 done | Then Kah Nyee , Ong Shern Wen Benjamin, Tan Xing Yu Jayden, Chen Jian Cong, Wong Zi Yang | 2023-08-12 | version2.1
Sprint | Week | Sprint Goal | Start Date | End Date | Sprint State
1 | 12/13 | - Create Readme.md file in Github -Write up code for REQ-02 to REQ-18 - Write manual test cases for REQ-02 to REQ-06 - Create tags 'version0.1', 'version0.2', and 'version0.3' - Update Use Diagrams in SRS Document - Create Release version1.0 in Github | 2023-07-03 | 2023-07-16 | Closed
2 | 14/15 | - Write up code for REQ-01, REQ-19, and REQ-20 - Write software unit test cases for REQ-07, REQ-11, REQ-15, and REQ-20 - Write manual test cases for REQ-01, REQ-08 to REQ-10, REQ-12 to REQ-14, REQ-16 to REQ-19, and REQ-21 - Create tags 'version1.1' and 'version1.2' - Update Use Diagrams in SRS Document - Create Release version2.0 in Github | 2023-07-17 | 2023-07-30 | Closed
3 | 16/17 | - Write up code to allow data transmission between main.py and app.py - Write manual test case for REQ-22 - Integration testing - Create Dockerfile and build Docker image - Docker container deployment test - Create tag 'version2.1' - Update Use Diagrams in SRS Document - Create Release version3.0 in Github | 2023-07-31 | 2023-08-13 | Active
Formulas:
Version = [Date]+13
Date = [Date, row above]+14

## Active Sprint Board (hidden)
To Do | Doing | Done

## Product Backlog
ID | Story Title | Story Description | Definition of Done | Estimated Effort (hours) | Actual Effort (hours) | Status | Sprint
1 | Create Use Case Diagrams in SRS document | As a Software Developer, I need to define all the different Use Case Diagrams for the Automated Gardening System | All necessary Use Case Diagrams are defined in the SRS document SRS document is commited and pushed to Github | 5 | 5 | Done | Sprint 1
2 | Create Readme.md file in GitHub | Readme.md file made to give a brief overview of the Automated Gardening System and its functions | Readme.md file is created with all parameters defined and project functions described Readme.md file is commited and pushed to Github | 1 | 0.5 | Done | Sprint 1
3 | Write up code for REQ-02 to REQ-06 | Write up code for REQ-02 to REQ-06 in main.py and debug the code if any bugs were to arise. | Codes for REQ-02 to REQ-06 are written with proper syntax in main.py and runs with no errors. main.py is commited and pushed to Github | 4 | 3 | Done | Sprint 1
4 | Tag current workflow as 'version0.1' | After REQ-02 to REQ-06 are implemented, Tag version0.1 is to be created. Current workflow should be tagged as "version0.1". | Tag is properly named as "version0.1" Tag "version0.1" is commited and pushed to Github | 0.1 | 0.1 | Done | Sprint 1
5 | Write up code for REQ-07 to REQ-18 | Write up code for REQ-07 to REQ-18 in their respective .py files and debug the code if any bugs were to arise. | Codes for REQ-07 to REQ-18 are written with proper syntax in their respective .py files and runs with no errors ec_level.py, light_intensity.py and temperature.py files commited and pushed to Github | 6 | 2 | Done | Sprint 1
6 | Tag current workflow as 'version0.2' | After REQ-07 to REQ-18 are implemented, Tag version0.2 is to be created. Current workflow should be tagged as "version0.2". | Tag is properly named as "version0.2" Tag "version0.2" is commited and pushed to Github | 0.1 | 0.1 | Done | Sprint 1
7 | Write manual test cases for REQ-02 to REQ-06 | As a Software Developer, I need to write up manual test cases for REQ-02 to REQ-06 to ensure that they are working as intended | Manual test cases for REQ-02 to REQ-06 to pass Manual test cases are given a 'Pass' in System Test Report | 3 | 2 | Done | Sprint 1
8 | Update Use Case Diagrams in SRS document | Use Case Diagrams in SRS document must be updated according to any changes that may arise | All necessary Use Case Diagrams are updated in the SRS document SRS document is commited and pushed to Github as the latest version | 1 | 2 | Done | Sprint 1
9 | Tag current workflow as 'version0.3' | After manual test cases for REQ-02 to REQ-06 have passed, Tag version0.3 is to be created. Current workflow should be tagged as "version0.3" | Tag is properly named as "version0.3" Tag "version0.3" is commited and pushed to Github | 0.1 | 0.1 | Done | Sprint 1
10 | Github release 'version1.0' created at the end of Sprint 1 | Release version1.0 should be created according to the latest tag "version0.3" at the end of Sprint 1 | Correct tag "version0.3" is used to publish release Github release is properly named as "version1.0" | 0.3 | 0.2 | Done | Sprint 1
11 | Write software unit test cases for REQ-07, REQ-11, REQ-15 | As a Software Developer, I need to write up software unit test cases for REQ-07, REQ-11, REQ-15 to ensure that they are working as intended | Software unit test cases for REQ-07, REQ-11, REQ-15 to pass Software unit test cases commited and pushed to Github | 4 | 1 | Done | Sprint 2
12 | Write manual test cases for REQ-08 to REQ-10, REQ-12 to REQ-14, REQ-16 to REQ-18 and REQ-21 | As a Software Developer, I need to write up manual test cases for REQ-08 to REQ-10, REQ-12 to REQ-14, REQ-16 to REQ-18 and REQ-21 to ensure that they are working as intended | Manual test cases for REQ-08 to REQ-10, REQ-12 to REQ-14, REQ-16 to REQ-18 and REQ-21 to pass Manual test cases are given a 'Pass' in System Test Report | 2 | 1 | Done | Sprint 2
13 | Tag current workflow as 'version1.1' | After manual test cases for REQ-08 to REQ-10, REQ-12 to REQ-14, REQ-16 to REQ-18 and REQ-21 and software unit test cases for REQ-07, REQ-11, and REQ-15 have passed, Tag version1.1 is to be created. Current workflow should be tagged as "version1.1". | Tag is properly named as "version1.1". Tag "version1.1" is commited and pushed to Github | 0.1 | 0.1 | Done | Sprint 2
14 | Write up code for REQ-01, REQ-19, REQ-20 | Write up code for REQ-01, REQ-19, REQ-20 in app.py and debug the code if bugs were to arise. | Codes for REQ-01, REQ-19, and REQ-20 are written with proper syntax in app.py and runs with no errors. The app.py is commited and pushed into github. | 4 | 8 | Done | Sprint 2
15 | Write manual test cases for REQ-01, REQ-19 | As a Software Developer, I need to write up manual test cases for REQ-01, REQ-19 to ensure that it is working as intended | Manual test cases for REQ-01, REQ-19 to pass Manual test cases is given a 'Pass' in System Test Report | 2 | 0.5 | Done | Sprint 2
16 | Write software unit test case for REQ-20 | As a Software Developer, I need to write up software unit test case for REQ-20 to ensure that it is working as intended | Software unit test case for REQ-20 to pass Software unit test cases commited and pushed to Github | 4 | 1 | Done | Sprint 2
17 | Update Use Case Diagrams in SRS document | Use Case Diagrams in SRS document must be updated according to any changes that may arise | All necessary Use Case Diagrams are updated in the SRS document SRS document is commited and pushed to Github as the latest version | 1 | 1 | Done | Sprint 2
18 | Tag current workflow as 'version1.2' | After manual test cases for REQ-01, REQ-19, and software unit test case for REQ-20 have passed, Tag version1.2 is to be created. Current workflow should be tagged as "version1.2". | Tag is properly named as "version1.2". Tag "version1.2" is commited and pushed to Github | 0.1 | 0.1 | Done | Sprint 2
19 | GitHub release 'version2.0' created at the end of Sprint 2 | Release version2.0 should be created according to the latest tag "version1.2" at the end of Sprint 2 | Correct tag "version1.2" is used to publish release Github release is properly named as "version2.0" | 0.3 | 0.3 | Done | Sprint 2
20 | Write up code to allow data tranmission between main.py and app.py | Extra code must be written in main.py and app.py to allow them to interact and exchange data with one another | main.py and app.py are able to interact with each other | 2 | 2 | Done | Sprint 3
21 | Write manual test case for REQ-22 | As a Software Developer, I need to write up manual test case for REQ-22 to ensure that it is working as intended | Manual test case for REQ-22 to pass Manual test case is given a 'Pass' in System Test Report | 1 | 1 | Done | Sprint 3
22 | Integration testing | All functions should be tested together to ensure that they work together as intended and can interact with one another without errors | All python files containing code for REQ-01 to REQ-20 are run together System is working as intended without any errors occurring. | 3 | 2 | Done | Sprint 3
23 | Create Dockerfile | Dockerfile to be created and image to be built | Container can be ran from docker image built with no errors. Dockerfile is commited and pushed to Github, Docker Image is pushed to DockerHub | 1 | 1 | Done | Sprint 3
24 | Docker container deployment test | Docker container must contain the required dependencies such that it can operate on the raspberry pi | Container can be built and ran on the raspberry pi with no errors. | 3 | 1 | Done | Sprint 3
25 | Update Use Case Diagrams in SRS document | Use Case Diagrams in SRS document must be updated according to any changes that may arise | All necessary Use Case Diagrams are updated in the SRS document SRS document is commited and pushed to Github as the latest version | 1 | 1 | Done | Sprint 3
26 | Tag current workflow as 'version2.1' | After Dockerfile has been implemented, Tag version2.1 is to be created. Current workflow should be tagged as "version2.1". | Tag is properly named as "version2.1". Tag "version2.1" is commited and pushed to Github | 0.1 | 0.1 | Done | Sprint 3
27 | GitHub release 'v3.0' created at the end of Sprint 3 | Release v3.0 should be created according to the latest tag "v2.1" at the end of Sprint 3 | Correct tag "version2.1" is used to publish release Github release is properly named as "version3.0" | 0.3 | 0.3 | Done | Sprint 3

## enum (hidden)
Sprint | Start Date | End Date | Story Status | Spint State
Sprint 1 |  |  | To Do | Inactive
Sprint 2 |  |  | Doing | Active
Sprint 3 |  |  | Done | Closed
Sprint 4
Sprint 5
Sprint 6