## Sprints
Sprint | Week | Sprint Goal | Start Date | End Date | Sprint State
1 | 12/13 | - Create Readme.md file in Github -Write up code for REQ-02 to REQ-18 - Write system test cases for REQ-02 to REQ-06 - Create tags 'version0.1', 'version0.2', and 'version0.3' - Create Release version1.0 in Github - Update Use Diagrams in SRS Document | 2023-07-03 | 2023-07-16 | Active
2 | 14/15 | - Write software unit test cases for REQ-07 to REQ-18 - Write up code for REQ-01, REQ-19, and REQ-20 - Create tags 'version1.1' and 'version1.2' - Create Release version2.0 in Github - Update Use Diagrams in SRS Document | 2023-07-17 | 2023-07-30 | Inactive
3 | 16/17 | - Write software unit test cases for REQ-01, REQ-19, and REQ-20 - Integration testing - Create tags 'version2.1' and 'version2.2' - Create Release version3.0 in Github - Update Use Diagrams in SRS Document | 2023-07-31 | 2023-08-13 | Inactive
Formulas:
End Date = [Start Date]+13
Start Date = [Start Date, row above]+14

## Active Sprint Board (hidden)
To Do | Doing | Done

## Product Backlog
ID | Story Title | Story Description | Definition of Done | Estimated Effort (hours) | Actual Effort (hours) | Status | Sprint
1 | Create Use Case Diagrams in SRS document | As a Software Developer, I need to define all the different Use Case Diagrams for the Automated Gardening System | All necessary Use Case Diagrams are defined in the SRS document SRS document is commited and pushed to Github | 5 | 5 | Done | Sprint 1
2 | Create Readme.md file in GitHub | Readme.md file made to give a brief overview of the Automated Gardening System and its functions | Readme.md file is created with all parameters defined and project functions described Readme.md file is commited and pushed to Github | 1 | 0.5 | Done | Sprint 1
3 | Write up code for REQ-02 to REQ-06 | Write up code for REQ-02 to REQ-06 in main.py and debug the code if any bugs were to arise. | Codes for REQ-02 to REQ-06 are written with proper syntax in main.py and runs with no errors. main.py is commited and pushed to Github | 4 | 3 | Done | Sprint 1
4 | Tag current workflow as 'version0.1' | After REQ-02 to REQ-06 are implemented, Tag version0.1 is to be created. Current workflow should be tagged as "version0.1". | Tag is properly named as "version0.1". Tag "version0.1" is commited and pushed to Github | 0.1 | 0.1 | Done | Sprint 1
5 | Write up code for REQ-07 to REQ-18 | Write up code for REQ-07 to REQ-18 in their respective .py files and debug the code if any bugs were to arise. | Codes for REQ-07 to REQ-18 are written with proper syntax in their respective .py files and runs with no errors. EC_level.py, Light_intensity.py and Temp.py files commited and pushed to Github | 6 | 2 | Done | Sprint 1
6 | Tag current workflow as 'version0.2' | After REQ-07 to REQ-18 are implemented, Tag version0.2 is to be created. Current workflow should be tagged as "version0.2". | Tag is properly named as "version0.2". Tag "version0.2" is commited and pushed to Github | 0.1 | 0.1 | Done | Sprint 1
7 | Write system test cases for REQ-02 to REQ-06 | As a Software Developer, I need to write up system tests for REQ-02 to REQ-06 to ensure that they are working as intended | System tests are working as intended All system tests for REQ-02 to REQ-06 to pass System test cases commited and pushed to Github | 3 | 2 | Done | Sprint 1
8 | Update Use Case Diagrams in SRS document | Use Case Diagrams in SRS document must be updated according to any changes that may arise | All necessary Use Case Diagrams are updated in the SRS document SRS document is commited and pushed to Github as the latest version | 1 | 2 | Done | Sprint 1
9 | Tag current workflow as 'version0.3' | After test cases for REQ-02 to REQ-06 are implemented, Tag version0.3 is to be created. Current workflow should be tagged as "version0.3". | Tag is properly named as "version0.3". Tag "version0.3" is commited and pushed to Github | 0.1 | 0.1 | Done | Sprint 1
10 | Github release 'version1.0' created at the end of Sprint 1 | Release version1.0 should be created according to the latest tag "version0.3" at the end of Sprint 1 | Correct tag "version0.3" is used to publish release Github release is properly named as "version1.0" | 0.3 | 0.2 | Done | Sprint 1
11 | Write up code for REQ-19 to REQ-20 | Write up code for REQ-19 to REQ-20 in Web_page.py and debug the code if bugs were to arise. | Codes for REQ-19 to REQ-20 are written with proper syntax in Web_page.py and runs with no errors. The Web_page.py is commited and pushed into github. | 4 |  | To Do | Sprint 2
12 | Write up code for REQ-01 | Write up code for REQ-01 in Web_page.py and debug the code if bugs were to arise. | Codes for REQ-01 are written with proper syntax in Web_page.py and runs with no errors. The Web_page.py is commited and pushed into github as the lastest version. | 1 |  | To Do | Sprint 2
13 | Tag current workflow as 'version1.1' | After REQ-01, REQ-19, and REQ-20 are implemented, Tag version1.1 is to be created. Current workflow should be tagged as "version1.1". | Tag is properly named as "version1.1". Tag "version1.1" is commited and pushed to Github | 0.1 |  | To Do | Sprint 2
14 | Write software unit test cases for REQ-07 to REQ-18 | As a Software Developer, I need to write up software unit tests for REQ-07 to REQ-18 to ensure that they are working as intended | Software unit tests are working as intended All software unit tests for REQ-07 to REQ-18 to pass The software unit tests commited and pushed to Github | 3 |  | To Do | Sprint 2
15 | Update Use Case Diagrams in SRS document | Use Case Diagrams in SRS document must be updated according to any changes that may arise | All necessary Use Case Diagrams are updated in the SRS document SRS document is commited and pushed to Github as the latest version | 1 |  | To Do | Sprint 2
16 | Tag current workflow as 'version1.2' | After test cases for REQ-07 to REQ-18 are implemented, Tag version1.2 is to be created. Current workflow should be tagged as "version1.2". | Tag is properly named as "version1.2". Tag "version1.2" is commited and pushed to Github | 0.1 |  | To Do | Sprint 2
17 | GitHub release 'version2.0' created at the end of Sprint 2 | Release version2.0 should be created according to the latest tag "version1.2" at the end of Sprint 2 | Correct tag "version1.2" is used to publish release Github release is properly named as "version2.0" | 0.3 |  | To Do | Sprint 2
18 | Write software unit test cases for REQ-01, REQ-19, and REQ-20 | As a Software Developer, I need to write up software unit tests for REQ-01, REQ-19, and REQ-20 to ensure that they are working as intended | Spftware unit tests are working as intended All software unit tests for REQ-01, REQ-19, and REQ-20 to pass The software unit tests commited and pushed to Github | 4 |  | To Do | Sprint 3
19 | Tag current workflow as 'version2.1' | After test cases for REQ-01, REQ-19, and REQ-20 are implemented, Tag version2.1 is to be created. Current workflow should be tagged as "version2.1". | Tag is properly named as "version2.1". Tag "version2.1" is commited and pushed to Github | 0.1 |  | To Do | Sprint 3
20 | Integration testing | All functions should be tested together to ensure that they work together as intended and can interact with one another without errors | All python files containing code for REQ-01 to REQ-20 are run together System is working as intended without any errors occurring. | 3 |  | To Do | Sprint 3
21 | Update Use Case Diagrams in SRS document | Use Case Diagrams in SRS document must be updated according to any changes that may arise | All necessary Use Case Diagrams are updated in the SRS document SRS document is commited and pushed to Github as the latest version | 1 |  | To Do | Sprint 3
22 | Tag current workflow as 'version2.2' | After integration testing and update of SRS document,Tag version2.2 is to be created. Current workflow should be tagged as "version2.2". | Tag is properly named as "version2.2". Tag "version2.2" is commited and pushed to Github | 0.1 |  | To Do | Sprint 3
23 | GitHub release 'v3.0' created at the end of Sprint 3 | Release v3.0 should be created according to the latest tag "v3.1" at the end of Sprint 3 | Correct tag "version2.2" is used to publish release Github release is properly named as "version3.0" | 0.3 |  | To Do | Sprint 3

## enum (hidden)
Sprint | Start Date | End Date | Story Status | Spint State
Sprint 1 |  |  | To Do | Inactive
Sprint 2 |  |  | Doing | Active
Sprint 3 |  |  | Done | Closed
Sprint 4
Sprint 5
Sprint 6